## Task_Table1
ID | Task_Name | Fixed_Cost | Fixed_Cost_Accrual | Total_Cost | Baseline | Variance | Actual | Remaining
0 | Tailspin Remote Drone | 0 | Prorated | 82314.554761904757 | 73370.054761904757 | 8944.5 | 59385.304761904757 | 22929.25
1 | Target Market Research and Analysis | 0 | Prorated | 19601.304761904761 | 18033.804761904761 | 1567.5 | 17351.304761904761 | 2250
2 | Research | 0 | Prorated | 11617.804761904763 | 11331.554761904763 | 286.25 | 9367.8047619047629 | 2250
3 | Research begins | 0 | Prorated | 0 | 0 | 0 | 0 | 0
4 | Surveys | 0 | Prorated | 2742.304761904762 | 2742.304761904762 | 0 | 2742.304761904762 | 0
5 | Develop survey questionnaire | 0 | Prorated | 1003.7333333333335 | 1003.7333333333335 | 0 | 1003.7333333333335 | 0
6 | Review and approval of survey | 0 | Prorated | 25 | 25 | 0 | 25 | 0
7 | Conduct survey | 0 | Prorated | 1713.5714285714287 | 1713.5714285714287 | 0 | 1713.5714285714287 | 0
8 | Focus Groups | 0 | Prorated | 3228 | 3228 | 0 | 2728 | 500
9 | Identify focus group member demographics | 0 | Prorated | 478 | 478 | 0 | 478 | 0
10 | Contact potential focus group members | 0 | Prorated | 1260 | 1260 | 0 | 1260 | 0
11 | Conduct focus groups | 0 | Prorated | 1490 | 1490 | 0 | 990 | 500
12 | Observations | 0 | Prorated | 5647.5 | 5361.25 | 286.25 | 3897.5 | 1750
13 | Identify observation parameters | 0 | Prorated | 145 | 145 | 0 | 145 | 0
14 | Select observation locations | 0 | Prorated | 72.5 | 36.25 | 36.25 | 72.5 | 0
15 | Conduct observations | 0 | Prorated | 5430 | 5180 | 250 | 3680 | 1750
16 | Research complete | 0 | Prorated | 0 | 0 | 0 | 0 | 0
17 | Analysis | 0 | Prorated | 7983.5 | 6702.25 | 1281.25 | 7983.5 | 0
18 | Analysis begins | 0 | Prorated | 0 | 0 | 0 | 0 | 0
19 | Analysis of Research Data | 0 | Prorated | 5408.5 | 4285.25 | 1123.25 | 5408.5 | 0
20 | Analyze surveys, focus groups, and observations | 0 | Prorated | 2296 | 1615.25 | 680.75 | 2296 | 0
21 | Create follow up actions for secondary research | 0 | Prorated | 490 | 490 | 0 | 490 | 0
22 | Conduct secondary research | 0 | Prorated | 2622.5 | 2180 | 442.5 | 2622.5 | 0
23 | Report of Research Findings | 0 | Prorated | 2575 | 2417 | 158 | 2575 | 0
24 | Compile draft copy of report | 0 | Prorated | 316.00000000000006 | 158.00000000000003 | 158.00000000000003 | 316.00000000000006 | 0
25 | Draft copy review period | 0 | Prorated | 1195 | 1195 | 0 | 1195 | 0
26 | Review comments and compile final report | 0 | Prorated | 1064 | 1064 | 0 | 1064 | 0
27 | Analysis complete | 0 | Prorated | 0 | 0 | 0 | 0 | 0
28 | Design | 0 | Prorated | 10900 | 8991 | 1909 | 10900 | 0
29 | Design begins | 0 | Prorated | 0 | 0 | 0 | 0 | 0
30 | Research Findings Evaluation | 0 | Prorated | 1342 | 1106 | 236 | 1342 | 0
31 | Design Document | 0 | Prorated | 916.00000000000011 | 916.00000000000011 | 0 | 916.00000000000011 | 0
32 | Proof of Concept | 0 | Prorated | 6730 | 6730 | 0 | 6730 | 0
33 | Final Design Selection | 0 | Prorated | 1912 | 239 | 1673 | 1912 | 0
34 | Design complete | 0 | Prorated | 0 | 0 | 0 | 0 | 0
35 | Product Development | 0 | Prorated | 25236 | 18622 | 6614 | 25236 | 0
36 | Product development begins | 0 | Prorated | 0 | 0 | 0 | 0 | 0
37 | Initial Prototype | 0 | Prorated | 8340 | 3860 | 4480 | 8340 | 0
38 | Internal Testing | 0 | Prorated | 10086 | 7242 | 2844 | 10086 | 0
39 | Raw Materials List | 0 | Prorated | 420 | 420 | 0 | 420 | 0
40 | Parts Designation | 0 | Prorated | 6390 | 7100 | -710 | 6390 | 0
41 | Product development complete | 0 | Prorated | 0 | 0 | 0 | 0 | 0
42 | Production Planning | 0 | Prorated | 10842 | 11001 | -159 | 4770 | 6072
43 | Production planning begins | 0 | Prorated | 0 | 0 | 0 | 0 | 0
44 | High-level Production Plan | 0 | Prorated | 6231 | 6390 | -159 | 4770 | 1461
45 | Resource Planning | 0 | Prorated | 4008 | 4008 | 0 | 0 | 4008
46 | Quality Control Design | 0 | Prorated | 444 | 444 | 0 | 0 | 444
47 | Final Production Plan Approval | 0 | Prorated | 159 | 159 | 0 | 0 | 159
48 | Production planning complete | 0 | Prorated | 0 | 0 | 0 | 0 | 0
49 | Marketing | 0 | Prorated | 13902.25 | 13902.25 | 0 | 0 | 13902.25
50 | Marketing phase begins | 0 | Prorated | 0 | 0 | 0 | 0 | 0
51 | Marketing Strategy Development | 0 | Prorated | 448.25 | 448.25 | 0 | 0 | 448.25
52 | Marketing Plan Development and Approval | 0 | Prorated | 764 | 764 | 0 | 0 | 764
53 | Marketing Materials | 0 | Prorated | 12690 | 12690 | 0 | 0 | 12690
54 | Marketing phase complete | 0 | Prorated | 0 | 0 | 0 | 0 | 0
55 | Project Management | 0 | Prorated | 1833 | 2820 | -987 | 1128 | 705
56 | Status Meeting | 0 | Prorated | 1833 | 2820 | -987 | 1128 | 705
57 | Status Meeting 1 | 0 | Prorated | 141 | 141 | 0 | 141 | 0
58 | Status Meeting 2 | 0 | Prorated | 141 | 141 | 0 | 141 | 0
59 | Status Meeting 3 | 0 | Prorated | 141 | 141 | 0 | 141 | 0
60 | Status Meeting 4 | 0 | Prorated | 141 | 141 | 0 | 141 | 0
61 | Status Meeting 5 | 0 | Prorated | 141 | 141 | 0 | 141 | 0
62 | Status Meeting 6 | 0 | Prorated | 141 | 141 | 0 | 141 | 0
63 | Status Meeting 7 | 0 | Prorated | 141 | 141 | 0 | 141 | 0
64 | Status Meeting 8 | 0 | Prorated | 141 | 141 | 0 | 141 | 0
65 | Status Meeting 9 | 0 | Prorated | 141 | 141 | 0 | 0 | 141
66 | Status Meeting 10 | 0 | Prorated | 141 | 141 | 0 | 0 | 141
67 | Status Meeting 11 | 0 | Prorated | 141 | 141 | 0 | 0 | 141
68 | Status Meeting 12 | 0 | Prorated | 141 | 141 | 0 | 0 | 141
69 | Status Meeting 13 | 0 | Prorated | 141 | 141 | 0 | 0 | 141
70 | Status Meeting 14 | 0 | Prorated | 0 | 0 | 0 | 0 | 0
71 | Status Meeting 15 | 0 | Prorated | 0 | 0 | 0 | 0 | 0
72 | Status Meeting 16 | 0 | Prorated | 0 | 0 | 0 | 0 | 0
73 | Status Meeting 17 | 0 | Prorated | 0 | 0 | 0 | 0 | 0
74 | Status Meeting 18 | 0 | Prorated | 0 | 0 | 0 | 0 | 0
75 | Status Meeting 19 | 0 | Prorated | 0 | 0 | 0 | 0 | 0
76 | Status Meeting 20 | 0 | Prorated | 0 | 0 | 0 | 0 | 0